## Dark
PROJECT: JKL Cleaning Service Web-based Platform
Client: JKL Cleaning Service |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
CPSY 301 G Group 6
Project start date: | 2024-01-08 |  |  |  |  | February | [13 empty] | March | [34 empty] | April
Scrolling increment: | 40 | time axis 2024-02-17 to 2024-04-12
Milestone description | Category | Assigned to | Progress | Start | Days | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
M1: Project Kickoff and Initial Planning | Milestone |  |  | 2024-01-15 | 1
Project kickoff meetings with JKL Cleaning Service. | Med Risk | Everyone | 30% | 2024-01-08 | 3
Formulate the project team, assign roles, and set communication protocols. | High Risk | Everyone | 50% | 2024-01-11 | 4
M2: Team Charter Finalization | Milestone |  | 0% | 2024-01-22 | 1
Finalize Team Charter with input from the team and sponsors. | Med Risk | Everyone | 70% | 2024-01-15 | 3
Ensure alignment between team expectations and project goals. | High Risk | Everyone | 50% | 2024-01-18 | 4
M3: Design Document Revision | Milestone |  |  | 2024-01-29 | 1
Finalize design document with overall structure and functionality. | Med Risk | Everyone | 80% | 2024-01-22 | 3
Collaborate with JKL Cleaning Service to gather input on key features. | High Risk | Everyone | 50% | 2024-01-25 | 4
M4: Client Design Review | Milestone |  |  | 2024-02-05 | 1
Present the final design document to JKL for review and feedback. | Med Risk | Everyone | 50% | 2024-01-29 | 3
Address concerns and suggestions, make necessary adjustments. | High Risk | Everyone |  | 2024-02-01 | 4
M5: Development - Online Booking Feature | Milestone |  |  | 2024-02-12 | 1
Continue Online Booking feature development, refining UI and functionality. | Med Risk | Sha, Lance |  | 2024-02-05 | 3
Integrate feature with secure database, conduct iterative testing. | High Risk | Sehaj, Nav |  | 2024-02-08 | 4
M6: Development - Employee Management Feature | Milestone |  |  | 2024-02-19 | 1 | bar: M
Progress with Employee Management portal development, ensuring secure logins. | Med Risk | Sha, Lance |  | 2024-02-12 | 3
Implement tools for Employees to track work hours and report progress. | High Risk | Sehaj, Nav |  | 2024-02-15 | 4
M7: Development - Employee Management Feature | Milestone |  |  | 2024-02-26 | 1 | bar: M
Continue refining Employee Management portal based on feedback. | Med Risk | Sha, Lance |  | 2024-02-19 | 3
Address outstanding issues related to schedule management and reporting tools. | High Risk | Sehaj, Nav |  | 2024-02-22 | 4
M8: Development - Notifications, Reviews, and Ratings Features | Milestone |  |  | 2024-03-04 | 1 | bar: M
Initiate development of customer notification systems. | Med Risk | Sha, Lance |  | 2024-02-26 | 3
Begin implementing Customer Reviews and Ratings feature, conduct initial testing. | High Risk | Sehaj, Nav |  | 2024-02-29 | 4
M9: Technical Design Review | Milestone |  |  | 2024-03-11 | 1
Conduct a technical design review to evaluate progress. | Med Risk | Sha, Lance |  | 2024-03-04 | 3
Discuss solutions for identified technical challenges, make adjustments. | High Risk | Sehaj, Nav |  | 2024-03-07 | 4
M10: Development - Notifications, Reviews, and Ratings Features | Milestone |  |  | 2024-03-18 | 1
Continue refining customer notification systems. | Med Risk | Sha, Lance |  | 2024-03-11 | 3
Enhance Customer Reviews and Ratings feature based on feedback. | High Risk | Sehaj, Nav |  | 2024-03-14 | 4
M11: Final Testing and Polishing | Milestone |  |  | 2024-04-01 | 1
Conduct comprehensive testing of all features. | Med Risk | Sha, Lance |  | 2024-03-18 | 7
Address remaining issues, bugs, and polish UI based on feedback. | High Risk | Sehaj, Nav |  | 2024-03-25 | 7
M12: Acceptance Test Plan and Beta Installation | Milestone |  |  | 2024-04-15 | 1
Develop acceptance test plan to validate all features. | Med Risk | Sha, Lance |  | 2024-04-01 | 7
Begin beta installation for initial testing, address feedback. | High Risk | Sehaj, Nav |  | 2024-04-08 | 7
M13: Final Presentation | Milestone | Everyone |  | 2024-04-22 | 1
JKL Platform Final Presentation Preparation | High Risk | Everyone |  | 2024-04-15 | 3

## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column